## Gantt Chart
	Schejewel				12%
	Schejewel.com
			Monday, February 09, 2015

										05					06					07					08					09					10					11					12					13					14					15					16					17					18					19					20					21					22					23					24					25					26					27					28					29					30
	Task Names	Resource Names	Start	Duration	Finish	% Complete	Calendar days	Days Completed	Days Remaining	Jan-15	Feb-15					Mar-15					Milestone 1.00					Apr-15		Milestone 1.10					Milestone 1.20					May-15					Jun-15					Jul-15
			31-Jan-2015	58	22-Apr-2015	12%	82			31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30

	Front End	[name]	31-Jan-2015	58	22-Apr-2015	13%	82	17	112
1.01	Return User token with privileges	[name]	Jan 31, 15	7	09-Feb-2015	100%	10	7	0
1.02	Create an API for returning data to daily page	[name]	Jan 31, 15	20	26-Feb-2015	25%	27	5	15
1.03	Create an API for returning data to monthly page		Jan 31, 15	20	26-Feb-2015	25%	27	5	15
1.04	API: Return a list of resources and there availability for a given day		Feb 28, 15	5	05-Mar-2015	0%	6	0	5
1.11	Change cruise line database when something is changed		Mar 7, 15	14	25-Mar-2015	0%	19	0	14
1.12	Poll cruise line database for changes to ship times		Mar 7, 15	21	03-Apr-2015	0%	28	0	21
1.13	Generate reports in a customizable printable PDF version		Mar 21, 15	14	08-Apr-2015	0%	19	0	14
1.21	Messaging system to communicate between users for resources		Apr 4, 15	14	22-Apr-2015	0%	19	0	14
1.22	Notifications if events have changed or conflicts arise	[name]	Apr 4, 15	14	22-Apr-2015	0%	19	0	14
1.23	Parse beginning of year pdf file for ports and cruise ship docking times		Apr 4, 15	14	22-Apr-2015	0%	19	0	14

	Back End	[name]	31-Jan-2015	48	08-Apr-2015	11%	68	11	108
1.05	Create HTTP redirect so all pages are handled with HTTPS	[name]	Jan 31, 15	7	09-Feb-2015	100%	10	7	0
1.06	Monthly schedule view	[name]	Jan 31, 15	28	10-Mar-2015	10%	39	2	26
1.07	Add Create resources page in wizard format		Jan 31, 15	28	10-Mar-2015	10%	39	2	26
1.08	Add a create tour type page for making generic tours		Feb 28, 15	7	09-Mar-2015	0%	10	0	7
1.14	Add ability to show available resources and view other users resources when allowed		Mar 7, 15	14	25-Mar-2015	0%	19	0	14
1.15	Add page to create and customize printable reports		Mar 7, 15	21	03-Apr-2015	0%	28	0	21
1.24	Add view for tours to be settled for both the excursion and cruise line		Mar 21, 15	14	08-Apr-2015	0%	19	0	14

	Database	[name]	31-Jan-2015	2	03-Feb-2015	85%	4	4	1
1.09a	Add database table creation files	[name]	Jan 31, 15	1	31-Jan-2015	100%	1	1	0
1.09b	Add testing database statements for creating and inserting the database	[name]	Jan 31, 15	3	03-Feb-2015	75%	4	2	1
1.09c	Secure server access to database		Jan 31, 15	1	31-Jan-2015	100%	1	1	0

	Milestones:
	1.00
	1.10
	1.20