## Gantt Chart
ID	Front End	Start	Duration(days)	End
1.01	Return User token with privileges	Jan 31, 15	7	09-Feb-2015
1.02	Create an API for returning data to daily page	Jan 31, 15	20	26-Feb-2015
1.03	Create an API for returning data to monthly page	Jan 31, 15	20	26-Feb-2015
1.04	API: Return a list of resources and there availability for a given day	Feb 28, 15	5	05-Mar-2015
1.05	Create HTTP redirect so all pages are handled with HTTPS	Jan 31, 15	7	09-Feb-2015
1.06	Monthly schedule view	Jan 31, 15	28	10-Mar-2015
1.07	Add Create resources page in wizard format	Jan 31, 15	28	10-Mar-2015
1.08	Add a create tour type page for making generic tours	Feb 28, 15	7	09-Mar-2015
1.09a	Add database table creation files	Jan 31, 15	1	31-Jan-2015
1.09b	Add testing database statements for creating and inserting the database	Jan 31, 15	3	03-Feb-2015
1.09c	Secure server access to database	Jan 31, 15	1	31-Jan-2015
1.11	Change cruise line database when something is changed	Mar 7, 15	14	25-Mar-2015
1.12	Poll cruise line database for changes to ship times	Mar 7, 15	21	03-Apr-2015
1.13	Generate reports in a customizable printable PDF version	Mar 21, 15	14	08-Apr-2015
1.14	Add ability to show available resources and view other users resources when allowed	Mar 7, 15	14	25-Mar-2015
1.15	Add page to create and customize printable reports	Mar 7, 15	21	03-Apr-2015
1.21	Messaging system to communicate between users for resources	Apr 4, 15	14	22-Apr-2015
1.22	Notifications if events have changed or conflicts arise	Apr 4, 15	14	22-Apr-2015
1.23	Parse beginning of year pdf file for ports and cruise ship docking times	Apr 4, 15	14	22-Apr-2015
1.24	Add view for tours to be settled for both the excursion and cruise line	Mar 21, 15	14	08-Apr-2015

	Milestones:
	1.00
	1.10
	1.20